## Read me
Employee Help: source tracker
Entirely fictional demonstration. No real employee, customer, financial or operational data.
Snapshot: end of 24 September 2026. Fixed review date: 25 September 2026.
24 tasks, six teams. Only IT Support and Workplace Services are in the approved pilot.
Team users are service participants, not staff assigned to deliver tasks.
Target: 12 October 2026. It is conditional, not a confirmed launch.
All eight pilot tasks T01-T08 are launch gates. Later-phase tasks do not enter pilot readiness counts.
Complete is the only completed status. Open, In progress and Blocked all remain incomplete.
Overdue means DueDate earlier than 25 September 2026 and Status is not Complete. Due on the review date is not overdue.
Dependencies are comma-separated task IDs. An incomplete prerequisite prevents its dependent task from being ready.
Blank Owner means no owner agreed. Do not infer one from the team lead.
Planning Meeting Notes.docx defines scope. Latest Update.docx changes only T06 and T07.
This file intentionally contains raw source records, not prebuilt charts, model answers or hidden formula caches.
Preserve this snapshot. Create a separate reconciled dataset in any generated dashboard or action plan.

## Teams
Team | Team lead | Users | Approved phase
IT Support | Colin Ballinger | 60 | Pilot
Workplace Services | Karin Blair | 40 | Pilot
People Operations | Alex Morgan | 80 | Later - not approved
Finance Operations | Taylor Reed | 50 | Later - not approved
Procurement | Jordan Ellis | 30 | Later - not approved
Sales Operations | Sam Lee | 70 | Later - not approved

## Tasks
TaskID | Team | Task | Owner | DueDate | Status | Phase | Pilot gate | DependsOn | Snapshot note
T01 | IT Support | Agree the request catalogue | Colin Ballinger | 2026-09-22 | Complete | Pilot | Yes |  | Request types agreed; equipment and account access only.
T02 | IT Support | Finish routing and escalation rules | Kadji Bell | 2026-09-24 | In progress | Pilot | Yes | T01 | Urgent requests still need a tested escalation path.
T03 | IT Support | Test pilot access | Kadji Bell | 2026-09-24 | Complete | Pilot | Yes |  | Access tested with the pilot group; no broad access granted.
T04 | IT Support | Confirm the support rota | Colin Ballinger | 2026-10-06 | Open | Pilot | Yes | T02 | Rota cannot be signed off before routing is settled.
T05 | Workplace Services | Agree facilities request categories | Karin Blair | 2026-09-23 | Complete | Pilot | Yes |  | Meeting-room support and building access requests agreed.
T06 | Workplace Services | Complete screen-reader walkthrough | Karin Blair | 2026-09-24 | Blocked | Pilot | Yes |  | Keyboard focus defect prevents completion in this snapshot.
T07 | Workplace Services | Train pilot coordinators | Karin Blair | 2026-10-07 | In progress | Pilot | Yes | T05 | Training session booked; attendance not yet completed.
T08 | Workplace Services | Approve pilot invite and help page | Colin Ballinger | 2026-10-09 | Open | Pilot | Yes | T02,T04,T06,T07 | Hold the announcement until all pilot gates are complete.
T09 | People Operations | Catalogue general HR questions | Alex Morgan | 2026-10-20 | Complete | Later - not approved | No |  | Later phase only; not part of the pilot.
T10 | People Operations | Define restricted case handling | Alex Morgan | 2026-10-21 | Open | Later - not approved | No | T09 | Sensitive employee cases are excluded from this demo pilot.
T11 | People Operations | Plan adviser training | Alex Morgan | 2026-10-22 | Open | Later - not approved | No | T10 | No rollout date approved.
T12 | People Operations | Prepare later-phase communications | Alex Morgan | 2026-10-23 | Open | Later - not approved | No | T11 | Draft only after later-phase approval.
T13 | Finance Operations | Catalogue expense and purchasing questions | Taylor Reed | 2026-10-20 | Complete | Later - not approved | No |  | Later phase only.
T14 | Finance Operations | Confirm finance service owner |  | 2026-09-24 | Blocked | Later - not approved | No | T13 | Missing owner is a later-phase issue, not a pilot blocker.
T15 | Finance Operations | Plan finance coordinator training | Taylor Reed | 2026-10-22 | Open | Later - not approved | No | T14 | No rollout date approved.
T16 | Finance Operations | Draft finance help content | Taylor Reed | 2026-10-23 | Open | Later - not approved | No | T15 | Later phase only.
T17 | Procurement | Catalogue supplier queries | Jordan Ellis | 2026-10-20 | Complete | Later - not approved | No |  | Later phase only.
T18 | Procurement | Define purchasing escalation | Jordan Ellis | 2026-10-21 | In progress | Later - not approved | No | T17 | No connection to a purchasing system has been approved.
T19 | Procurement | Plan buyer training | Jordan Ellis | 2026-10-22 | Open | Later - not approved | No | T18 | No rollout date approved.
T20 | Procurement | Draft procurement help content | Jordan Ellis | 2026-10-23 | Open | Later - not approved | No | T19 | Later phase only.
T21 | Sales Operations | Catalogue sales support requests | Sam Lee | 2026-10-20 | Complete | Later - not approved | No |  | Later phase only.
T22 | Sales Operations | Nominate a sales coordinator |  | 2026-09-24 | Blocked | Later - not approved | No | T21 | Missing owner is a later-phase issue, not a pilot blocker.
T23 | Sales Operations | Plan sales coordinator training | Sam Lee | 2026-10-22 | Open | Later - not approved | No | T22 | No rollout date approved.
T24 | Sales Operations | Draft sales support help content | Sam Lee | 2026-10-23 | Open | Later - not approved | No | T23 | Later phase only.